## Estimate
BS Units ¦ UI fix estimate
Planning date | 2026-10-05
Task count | 32
Base effort (h) | 198
Contingency | 20%
Planned effort (h) | 237.6
Productive hours / day | 6
Working days, 1 developer | 40
Working weeks, 5 days | 8
Delivery order | Tasks | Design h | Flutter h | QA h | Base total h
Foundation | 4 | 8 | 15 | 4 | 27
Core screens | 9 | 12 | 32 | 9 | 53
Authentication | 3 | 4 | 12 | 3 | 19
Requests | 8 | 9.5 | 32.5 | 10 | 52
Secondary screens | 6 | 6 | 17 | 6 | 29
Visual QA | 2 | 0 | 10 | 8 | 18
Total | 32 | 39.5 | 118.5 | 40 | 198
Scope and estimate basis
UI only: visual design, styling, spacing, typography, existing screen layouts and visual QA.
Preserve routes, API calls, business rules, permissions and calculation logic. No new features.
Basis: repository source review and existing home.png / screen.png; no live app audit performed.
Estimates are planning judgments for one Flutter developer; design and QA effort are included per task.
QA rows cover cross-screen checks; per-task QA covers the individual revised screen or component.
20% contingency covers visual iteration and device differences; no review waiting time is included.
Assume existing assets, English/Khmer support and Android/iOS access; brand approval may change effort.
Edit amber estimates, status and owner on UI Tasks; edit contingency and daily capacity here.
Rows are grouped by delivery phase. Complete dependency IDs before their dependent tasks.
Re-estimate after reviewing mockups and the running app. No start date or deadline has been assumed.

## UI Tasks
BS Units ¦ UI fix backlog
Estimates are person-hours. Amber cells are editable; Total h is calculated. P1 first, P2 next, P3 polish.
ID | Phase | Priority | UI task | Proposed fix | Acceptance criteria | Design h | Flutter h | QA h | Total h | Depends on | Status | Owner | Source / evidence
UI-01 | Foundation | P1 | Define visual direction | Agree palette, typography, spacing, cards and buttons using Home and login mockups. | Two screen mockups and shared style rules reviewed. | 4 | 0 | 1 | 5 | — | Not started |  | lib/app/theme/app_theme.dart
UI-02 | Foundation | P1 | Replace placeholder theme | Implement brand colors, type scale, surfaces, borders and component themes. | Shared theme drives text, fields, buttons, cards and app bars. | 2 | 5 | 1 | 8 | UI-01 | Not started |  | lib/app/theme/app_theme.dart
UI-03 | Foundation | P1 | Create shared UI components | Standardize screen padding, section titles, search fields, status badges and action buttons. | Reusable components replace repeated visual patterns. | 1 | 6 | 1 | 8 | UI-02 | Not started |  | lib/core/widgets/; lib/features/*/views/
UI-04 | Foundation | P1 | Style loading, empty and error states | Apply consistent visual states to existing loading/error conditions without changing data logic. | Existing states have readable messages and stable layouts. | 1 | 4 | 1 | 6 | UI-03 | Not started |  | lib/features/*/views/
UI-05 | Core screens | P1 | Polish navigation and app bars | Restyle Home/More navigation, title alignment and action spacing; preserve destinations. | Selected tab is clear; labels and titles fit safe areas. | 1 | 3 | 1 | 5 | UI-02 | Not started |  | lib/app/views/main_shell.dart
UI-06 | Core screens | P1 | Redesign Home project list | Improve project card hierarchy, logo treatment, section spacing and header actions. | Long names fit; rows align; existing project navigation works. | 2 | 5 | 1 | 8 | UI-03 | Not started |  | lib/features/home/views/home_view.dart
UI-07 | Core screens | P2 | Polish Home banner carousel | Tune banner proportions, spacing, corners and image fallback presentation. | Banners avoid distortion; missing images retain a useful layout. | 1 | 2 | 1 | 4 | UI-06 | Not started |  | lib/features/home/views/home_view.dart
UI-08 | Core screens | P1 | Redesign project details | Improve unit-type chips, section headings, search field and unit rows. | Unit names and statuses are scannable without clipping. | 2 | 5 | 1 | 8 | UI-03 | Not started |  | lib/features/projects/views/project_detail_view.dart
UI-09 | Core screens | P1 | Polish unit search | Restyle app-bar search and results with consistent row and badge layout. | Keyboard and long queries do not hide or clip search controls. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/projects/views/unit_search_view.dart
UI-10 | Core screens | P1 | Redesign unit details and actions | Group status and existing actions; improve hierarchy and button spacing. | Existing action eligibility is preserved; key actions are clear. | 2 | 4 | 1 | 7 | UI-03 | Not started |  | lib/features/projects/views/unit_detail_view.dart
UI-11 | Core screens | P2 | Polish comments and photos | Improve composer, attachment thumbnails, remove controls and comment separation. | Photo controls are visible; composer fits small screens. | 1 | 4 | 1 | 6 | UI-10 | Not started |  | lib/features/projects/views/unit_detail_view.dart
UI-12 | Core screens | P2 | Polish unit-type details | Improve hero image proportions, metadata sections and related unit rows. | Image fallback and long text maintain consistent spacing. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/projects/views/unit_type_detail_view.dart
UI-13 | Core screens | P2 | Polish units grouped by status | Improve status section headers and wrapped unit chips; retain grouped-list layout. | Groups remain readable; status has text as well as color. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/projects/views/floor_plan_view.dart
UI-14 | Authentication | P1 | Redesign login | Use existing logo, stronger hierarchy, consistent fields and primary action styling. | Login fits keyboard-open and small-screen layouts. | 2 | 4 | 1 | 7 | UI-02 | Not started |  | lib/features/auth/views/login_view.dart
UI-15 | Authentication | P2 | Polish password screens | Apply consistent step headings, fields, error presentation and submit buttons. | Reset/change-password stages remain readable and usable. | 1 | 4 | 1 | 6 | UI-03 | Not started |  | lib/features/auth/views/forgot_password_view.dart; change_password_view.dart
UI-16 | Authentication | P2 | Polish profile and members | Improve avatar, account sections, edit controls and member rows. | Profile actions and member names fit without overlap. | 1 | 4 | 1 | 6 | UI-03 | Not started |  | lib/features/auth/views/profile_view.dart; members_view.dart
UI-17 | Requests | P1 | Polish Hold request list | Improve search, request row hierarchy, status badges and existing action layout. | Requests and actions fit long labels and empty results. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/hold/views/hold_view.dart
UI-18 | Requests | P1 | Polish Deposit request list | Improve search, status, request metadata and existing action layout. | Deposit actions remain available under existing conditions. | 1 | 4 | 1 | 6 | UI-03 | Not started |  | lib/features/deposit/views/deposit_view.dart
UI-19 | Requests | P1 | Polish Contract request list | Improve search, rows, status and document/action affordances. | Contract entries and existing actions are visually distinct. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/contract_request/views/contract_request_view.dart
UI-20 | Requests | P2 | Polish Hold request form | Group unit summary, reason field, errors and submit action. | Keyboard-safe layout; existing errors appear close to the form. | 1 | 2 | 1 | 4 | UI-03 | Not started |  | lib/features/hold/views/hold_request_form_view.dart
UI-21 | Requests | P1 | Redesign Deposit request form | Section customer, payment and optional partner fields; improve labels and spacing. | Every existing field is retained; expanded sections remain readable. | 2 | 8 | 2 | 12 | UI-03 | Not started |  | lib/features/deposit/views/deposit_request_form_view.dart
UI-22 | Requests | P1 | Polish change-unit/deposit form | Improve unit selection, terms, payment sections and optional partner layout. | Search results and expanded fields fit keyboard-open layouts. | 2 | 6 | 2 | 10 | UI-21 | Not started |  | lib/features/deposit/views/change_unit_deposit_view.dart
UI-23 | Requests | P1 | Polish Contract request form | Improve deposit summary, date rows, attachment controls and submit action. | Dates are clear; attachment removal controls do not clip. | 1 | 5 | 1 | 7 | UI-03 | Not started |  | lib/features/contract_request/views/contract_request_form_view.dart
UI-24 | Requests | P2 | Polish contract viewer shell | Style app bar and existing loading/error presentation around PDF viewer. | Viewer uses available space; loading/error text is readable. | 0.5 | 1.5 | 1 | 3 | UI-02 | Not started |  | lib/features/contract_request/views/contract_pdf_view.dart
UI-25 | Secondary screens | P2 | Group and polish More menu | Add visual group hierarchy, consistent icons and row spacing; retain routes. | Account, requests and tools are easy to scan. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/more/views/more_view.dart
UI-26 | Secondary screens | P2 | Polish notifications | Improve notification row spacing, text hierarchy and existing read-state styling. | Long messages and timestamps fit without overlap. | 1 | 2 | 1 | 4 | UI-03 | Not started |  | lib/features/notification/views/notification_view.dart
UI-27 | Secondary screens | P2 | Polish announcements and detail | Improve image cards, title/body hierarchy and image error placeholders. | Missing images do not create blank visual gaps. | 1 | 4 | 1 | 6 | UI-03 | Not started |  | lib/features/post/views/post_view.dart; post_detail_view.dart
UI-28 | Secondary screens | P2 | Polish loan calculator | Group inputs and present existing calculation results in a clear result panel. | Values and units align; existing calculation behavior is preserved. | 1 | 2 | 1 | 4 | UI-03 | Not started |  | lib/features/more/views/loan_calculator_view.dart
UI-29 | Secondary screens | P3 | Polish scanner, support and About | Improve scanner prompts, support action rows and About branding. | Existing actions remain visible; layouts follow the shared theme. | 1 | 3 | 1 | 5 | UI-03 | Not started |  | lib/features/more/views/document_scanner_view.dart; support_center_view.dart; about_view.dart
UI-30 | Secondary screens | P2 | Polish splash and app dialogs | Use existing logo on splash; style app-owned update/reason dialogs and snackbars. | Dialog content fits; system permission dialogs remain OS-controlled. | 1 | 3 | 1 | 5 | UI-02 | Not started |  | lib/features/splash/views/splash_view.dart; lib/core/widgets/reason_dialog.dart; lib/features/auth/controllers/auth_controller.dart
UI-31 | Visual QA | P1 | Fix responsive and language layout issues | Review all revised screens at 320/360/390/430 logical-pixel widths in English and Khmer. | No overflow, clipped Khmer glyphs, hidden actions or keyboard obstruction. | 0 | 6 | 4 | 10 | UI-05–UI-30 | Not started |  | lib/features/*/views/; lib/l10n/
UI-32 | Visual QA | P1 | Verify accessibility and final visual consistency | Check contrast, touch targets, large text and revised screens on Android and iOS. | Text contrast >=4.5:1; controls >=48 logical pixels; 1.3x text fits. | 0 | 4 | 4 | 8 | UI-31 | Not started |  | lib/app/theme/; lib/features/*/views/